## Sheet1
Tasks | Week started | Weeks to complete
Started: 06/10/2025
RESEARCH | 0 | 8
Security Enhanced Linux | 0 | 3
Chinese Wall Policy | 3 | 2
Linux system daemons | 5 | 3
EXPERIMENTATION | 1 | 8
Red Hat environment setup with virt manager | 1 | 1.5
Exploring SELinux capabilities | 2.5 | 2
Static Chinese Wall complete | 4.5 | 4.5
DESIGN | 6 | 4
Chinese Wall daemon functional requirements | 6 | 3
Chinese Wall daemon technical specification | 9 | 1
Design Complete | 10 | 0.5
IMPLEMENTATION | 9 | 10
Core daemon confined by SElinux complete | 9 | 1.5
Implenent subject monitoring | 10.5 | 2
Implement conflict of interest identification | 12.5 | 1.5
Develop policy engine | 14 | 4.5
Chinese Wall daemon complete | 18.5 | 0.5
TESTING | 11.5 | 8.5
Test subjects correctly monitored | 11.5 | 1.5
Test dynamic chinese wall works | 16 | 3
Test daemon is efficient & safe | 19 | 1
All tests passed | 20 | 0.5
WRITEUP | 5 | 20
November progress report | 5 | 9
Presentation | 22 | 3
Final report | 15 | 10
Completed submission | 24.5 | 0.5
Complete: 30/03/2026